## Sheet1
TEST CASE
Project Name |  | www.goinnovior.com |  |  | Project Description |  | Corporate Website
Project Manager |  | Tasnia Afrin Asha |  |  | Technology Used |  | HTML, CSS,Bootstrap,ReactJS,VueJS,ExpressJS,MongoDB
Expected Starting Date |  | 2024-04-24 |  |  | Actual Starting Date |  | 2024-04-24
expected Completion Date |  | 2024-06-24 |  |  | Actual Completion Date
SL | Module/Feature/Page Name | Test Case ID | Test Case Title | Test Data / Information | Test Step | Expected Result | Actual Result | Status | Data/Input Data | Comment
1 | Verify Home Page load | TC001 | Loading Page | N/A | 1. Ensure Internet Connectivity 2. Write the following url in the Browser www.goinnovior.com 3. Press Enter | The Landing Page Should be loaded Succesfully | As Excepted | Pass | N/A
2 |  | TC002 | Inspect Top Header's Element (Mobile Number) for Desktop view | N/A | 1. Click on mobile number/icon | It Should take to the calling interface available in your local Sysytem | As Excepted | pass | N/A
3 |  | TC003 | Inspect Top Header's Element (Email Id) for Desktop view test case on the basis of windows operating system | N/A | 1. Click on Email ID/Icon | It Should take to the default email interface | As Excepted | pass | N/A | If you are not login the interface , then Login the account
4 |  | TC004 | Inspect Top Header's Element (Email Id) for Desktop view test case on the basis of MAC operating system | N/A | 1. Click on Email ID/Icon | It Shouldn't take to the default email interface | Not Excepted | Fail | N/A | 1. For chrome its doesn't work 2. As a default works in safari browser
5 |  | TC005 | Inspect Top Header's Element (Facebook Link) for Desktop view | N/A | 1. click on Facebook Icon | It should take to the default facebook interface | As Excepted | pass | N/A | If you are not login the interface , then Login the account
6 |  | TC006 | Inspect Top Header's Element (Instagram) for Desktop view | N/A | 1. Click on Instagram Icon | It Shouldn't take to the default Instagram interface | As Excepted | pass | N/A
7 |  | TC007 | Inspect Top Header's Element (Linkedin) for Desktop view | N/A | 1. Click on Linkedin Icon | It should take to the default facebook interface | As Excepted | pass | N/A | If you are not login the interface , then Login the account
8 |  | TC008 | Inspect Top Header's Element (Twitter) for Desktop view | N/A | 1. Click on Twitter Icon | It should take to the default X interface | As Excepted | pass | N/A | If you are not login the interface , then Login the account
9 | Check Navigation Menu | TC009 | Explore us for Desktop View | N/A | 1. Click on Explore us in this website | It take to the default Explore us webpage | As Excepted | pass | N/A
10 |  | TC010 | Services for Desktop View | N/A | 1. Click on Services in this website 2. Select Category | It take to the default Services webpage | As Excepted | pass | N/A
11 |  | TC011 | Solutions for Desktop View | N/A | 1. Click on Solutions in this website 2. Select Category | It take to the default Solutions webpage | AS Excepted | pass | N/A
12 |  | TC012 | Latest Articles for Desktop View | N/A | 1. Click on Latest Articles in this website 2. Select Category | It take to the default Latest Articles webpage | AS Excepted | pass | N/A
13 |  | TC013 | Career for Desktop View | N/A | 1. Click on Career in this website | It take to the default Career webpage | AS Excepted | pass | N/A
14 |  | TC014 | Contract for Desktop View | N/A | 1. Click on Contract in this website | It take to the default Contract webpage | AS Excepted | pass | N/A
15 |  | TC015 | Brochure Download | N/A | 1. Click on the Brochure download button | It take to the default Brochure Download page | AS Excepted | Fail | N/A | 1. This company brochures are not updated. 2. Please Upload the Update Brochures
16 |  | TC016 | Nine Dots | N/A | 1. Click on the Nine Dots Button | It take to the default Contents page | Not Excepted | Fail | N/A | Nine Dots section are empty. There are no contents available in this page
17 | Functional Links and Button | TC017 | How we Serve | N/A | 1. Click on the How we serve Button | It take to the default Button page | Not Excepted | Fail | N/A
18 |  | TC018 | Learn More Us | N/A | 1. Click on theLearn More Us Button | It take to the default learn more us page | Not Excepted | Fail | N/A
19 |  | TC019 | See More | N/A | 1. Click on the See More Button | It take to the default see more page | AS Excepted | pass | N/A
20 |  | TC020 | Request Consultation | N/A | 1. Click on the Request Consultation Button 2. Fill up the requerment 3. Click the Submit Button | It take to the default Request Consultation page | AS Excepted | pass | N/A
21 |  | TC021 | Whatsapp | N/A | 1. Click on the whatsapp contract button 2. Click on Continue to Chat | It take to the default whatsapp contract page | AS Excepted | pass | N/A
22 | Home > Career | TC022 | Employee details button (More Details) | N/A | 1. Click on the more details button | It take to the default employee details pages | AS Excepted | pass | N/A
23 |  | TC023 | Employee Jobs apply form | N/A | 1. Fill up the apply for the position form 2. Choose file (Select Picture to the device or drive) | Successfully fillup the form | AS Excepted | pass | N/A
24 |  | TC024 | Employee form Submit Button | N/A | 1. Click on the Submit button | Successfully added the information | AS Excepted | pass | N/A
25 | Home > Contract > Form | TC025 | Email feild Input | N/A | Write the Email Address | Input valid mail | Not Excepted | Fail | N/A | ALL email are worked , please confirmation is mail Valid or invalid
26 |  | TC026 | Phone Number Input | N/A | Write the Phone number | Input valid number | AS Excepted | pass | N/A
27 |  | TC027 | Official Website | N/A | Write the official mail address | Input Valid Email address | Not Excepted | Fail | N/A | ALL email are worked , please confirmation is mail Valid or invalid
28 |  | TC028 | Full Name | N/A | Write the Full Name | Input Correct Name | As Excepted | pass | N/A
29 |  | TC029 | Service types | N/A | Select the Service types | Input the Service types | As Excepted | pass | N/A
|  | TC030 | Message | N/A | Input any kind of message | Show the message | As Excepted | pass | N/A